## Sheet1
Task Name | Duration | Predecessors
MEMD/WRKS/2025-2026/00017 | 491 days
CONTRACT EFFECTIVENESS | 70 days
Contract Formalization | 70 days
Contract Signing | 5 days
Submission of Advance and perfomance securities, insurance bonds | 5 days | 4
Receipt of Advance | 60 days | 5
Kick-off Meeting and Site Possession | 6 days
Kick off meeting | 1 day | 4
Stakeholder sensitization (Site Launch) | 5 days | 8
DETAILED DESIGNS, SURVEY AND APPROVALS | 49 days
Design, Survey, RTK Profiling and Geo-Studies | 25 days
Satellite images, geo-referencing and critical locations | 21 days | 9
Preliminary survey, final image drawings and line designs | 14 days | 9
Bush Clearance, Pegging and Line Profiling using High Precision Equipment (RTK) | 14 days | 13SS
Production of Line profiles, conductor sag-tension charts, and structural calculations. | 14 days | 14SS+7 days
33/11kV GIS substation design (SLDs, layout, earthing, protection design) and Telecom/SCADA architecture design. | 14 days | 14SS+7 days
Substation civil works design and design calculations, Substation topographical survey and geotechnical investigations. | 7 days | 14SS
33kV cable route evaluation and earthing studies | 7 days | 17SS
Preparation of design drawings | 18 days | 17
Design Review and Approval | 24 days
Submission of all preliminary designs, SLDs, route drawings, civil works plans, and ITPs | 3 days | 19
Employer review and approval cycles. | 14 days | 21
Finalization of construction access routes, land entry protocols, and preliminary stakeholder engagements. | 7 days | 22
MATERIAL PROCUREMENT AND DELIVERY | 260 days
Treated Wooden poles-Buyara -Uganda | 56 days
Order placement and confirmation | 5 days | 22
Manufacture | 45 days | 26
Routine Tests Acceptance by Employer (for each batch produced) | 35 days | 27SS+15 days
Transportation to site | 35 days | 28SS+1 day
Concrete poles-Delta Link-Uganda | 76 days
Order placement and confirmation | 5 days | 22
Manufacture | 60 days | 31
Routine Tests Acceptance by Employer (for each batch produced) | 55 days | 32SS+15 days
Transportation to site | 55 days | 33SS+1 day
AAAC conductor and ABC Cables- Seven Hills-Uganda | 101 days
Order placement and confirmation | 5 days | 22
Manufacture | 90 days | 36
Routine Tests Acceptance by Employer (for each batch produced) | 80 days | 37SS+15 days
Transportation to site | 80 days | 38SS+1 day
Distribution Transformers- Orion, Farady -Uganda | 101 days
Order placement and confirmation | 5 days | 22
Manufacture | 90 days | 41
Routine Tests Acceptance by Employer (for each batch produced) | 80 days | 42SS+15 days
Transportation to site | 80 days | 43SS+1 day
Stay Assembly, Earth wire, Insulators, Overhead Line Accessories, Switchgears and connection materials-Laurence- China | 120 days
Order placement and confirmation | 5 days | 22,6
Manufacture | 45 days | 46
Factory Acceptance Tests | 7 days | 47
Shipment | 28 days | 48
Customs Clearance | 21 days | 49
Delivery to site | 14 days | 50
LV Feeder Pillars- Powertech India | 135 days
Order placement and confirmation | 5 days | 22,6
Manufacture | 60 days | 53
Factory Acceptance Tests | 7 days | 54
Shipment | 28 days | 55
Customs Clearance | 21 days | 56
Delivery to site | 14 days | 57
Underground cables & OPGW- (Henan Qifan Electric Co. Ltd. -China) | 135 days
Order placement and confirmation | 5 days | 22,6
Manufacture | 60 days | 60
Factory Acceptance Tests | 7 days | 61
Shipment | 28 days | 62
Customs Clearance | 21 days | 63
Delivery to site | 14 days | 64
Autoreclosers- (Noja Power-Australia) | 135 days
Order placement and confirmation | 5 days | 22,6
Manufacture | 60 days | 67
Factory Acceptance Tests | 7 days | 68
Shipment | 28 days | 69
Customs Clearance | 21 days | 70
Delivery to site | 14 days | 71
Metering Units- (Macroplast-India) | 105 days
Order placement and confirmation | 5 days | 22,6
Manufacture | 30 days | 74
Factory Acceptance Tests | 7 days | 75
Shipment | 28 days | 76
Customs Clearance | 21 days | 77
Delivery to site | 14 days | 78
DC Battery Charger | 135 days
Order placement and confirmation | 5 days | 22,6
Manufacture | 60 days | 81
Factory Acceptance Tests | 7 days | 82
Shipment | 28 days | 83
Customs Clearance | 21 days | 84
Delivery to site | 14 days | 85
Diesel Generator | 135 days
Order placement and confirmation | 5 days | 22,6
Manufacture | 60 days | 88
Factory Acceptance Tests | 7 days | 89
Shipment | 28 days | 90
Customs Clearance | 21 days | 91
Delivery to site | 14 days | 92
33kV GIS for Buloba and Matugga Extensions-ABB Turkey & ABB China | 243 days
Order placement and confirmation | 5 days | 22,6
Manufacture | 160 days | 95
Factory Acceptance Tests | 15 days | 96
Shipment | 28 days | 97
Customs Clearance | 21 days | 98
Delivery to site | 14 days | 99
33 & 11kV GIS & SCADA, RMU& other accessories for Kampiringisa SS- Toshiba Malaysia | 243 days
Order placement and confirmation | 5 days | 22,6
Manufacture | 160 days | 102
Factory Acceptance Tests | 15 days | 103
Shipment | 28 days | 104
Customs Clearance | 21 days | 105
Delivery to site | 14 days | 106
Power Transformers-15/20MVA-Hitachi Vietnam | 235 days
Order placement and confirmation | 5 days | 22,6
Manufacture | 160 days | 109
Factory Acceptance Tests | 7 days | 110
Shipment | 28 days | 111
Customs Clearance | 21 days | 112
Delivery to site | 14 days | 113
Power Transformers-1MVA & 5MVA-India | 207 days
Order placement and confirmation | 5 days | 22,6
Manufacture | 150 days | 116
Factory Acceptance Tests | 7 days | 117
Shipment | 28 days | 118
Customs Clearance | 10 days | 119
Delivery to site | 7 days | 120
CONSTRUCTION OF HV & LV LINES, & SUBSTATION | 396 days
Mobilization | 51 days
Mobilization of project management team, engineers, surveyors, Enironmentalist, HSE officers, QA/QC personnel, and site supervisors. | 7 days | 8
Deployment of construction equipment, excavators, cranes, winches, tensioners, vehicles, lifting tools, linesman tools, and civil/building materials | 21 days | 124
Establishment of site office, storage yard, security systems, communication systems, and worker accommodation where required. | 30 days | 125SS
Opening of project registers, QA/QC systems, HSE systems, and documentation workspaces. | 14 days | 126
HV & LV Line construction | 189 days
Pole positioning | 90 days | 29SS+2 days,34SS+2 days,123
Pole erection and backfilling. | 100 days | 129SS
Stay Assembly, dressing and hardware installation. | 60 days | 51130
Stringing of AAAC 150/100 conductors on 33kV and LV ABC on associated routes. | 60 days | 131SS,39
OPGW installation tensioning, joint boxes, and termination. | 60 days | 65,132SS
Sagging, tensioning, jointing, and line finishing. | 60 days | 130SS,131SS
Cable Crossing structures at roads, HV Lines, etc. | 10 days | 134
Substation Civil works | 154 days
Control building Construction- setting out, walls, roofing, plastering, and finishing. | 75 days | 123
Transformer bund walls and oil containment system, Plinths. | 30 days | 137
Cable trench concreting, ducts, culverts, and drainage channels. | 21 days | 138
Yard surfacing, gravel filling, and fencing installation. | 28 days | 139
Underground Cable Works | 45 days
Trench excavation, sand bedding, cable laying. | 45 days | 65140
Installation of cable markers, tiles, warning tape. | 45 days | 142SS
Cable jointing, termination kits, and continuity tests. | 45 days | 143SS
Substation Equipment Installation | 53 days
Installation of GIS panels, busbars, disconnectors, and circuit breakers. | 37 days | 100107140144
Erection of 33/11kV 15/20MVA transformer and 5MVA transformers. | 45 days | 114121
Installation of surge arrestors, CTs, VTs, and gantry structures. | 45 days | 147SS
Assembly and wiring of protection and control panels. | 45 days | 147SS,148SS,146SS
Earthing & Lightning Protection | 150 days
Complete installation of earthing mesh/grid. | 60 days | 136
Continous Testing of earth resistance values for all equipment. | 90 days | 151
Lightning masts and down-conductors installation. | 90 days | 151
SCADA, Telecom & OPGW Integration | 44 days
Fiber splicing, OTDR tests. | 15 days | 133145150
Installation of SCADA servers, BCUs, gateways, etc | 30 days | 145
Testing of IEDs, time synchronization, communication mapping, and control room setup. | 14 days | 156
Testing, Protection, Commissioning & Final Works | 47 days
MV/LV Line Testing | 30 days
Line patrols, clearance verification, insulation checks. | 30 days | 128154
Earth resistance testing. | 30 days | 160SS
Load balancing and phase sequence testing for LV networks. | 30 days | 160SS
Substation Testing & Protection Settings | 30 days
Primary injection tests for CTs/VTs and busbars. | 15 days | 145154
Secondary injection tests for relays: differential, REF, O/C, EF, distance, breaker fail. | 15 days | 164SS
On-site Transformer testing (IR Test, Ratio test, winding resostance testc, functional testing for interlocks and trip circuits) | 15 days | 147150165
SCADA & Remote Control Commissioning | 7 days
End-to-end control tests with NCC. | 7 days | 166
Verification of analog and digital signals. | 7 days | 168SS
Remote operation tests of breakers and isolators. | 7 days | 169SS
Integrated System Commissioning | 10 days
Combined line, substation, protection, SCADA testing. | 5 days | 167
Energization in phases under Employer supervision. | 5 days | 172
Reliability tests | 5 days | 172
Handover, Documentation & Demobilization | 42 days
Final Documentation | 15 days
As-built drawings (CAD, PDF, GIS forms). | 15 days | 158
Test and commissioning reports. | 15 days | 177SS
O&M manuals for all equipment. | 15 days | 177SS
Factory certificates and warranties. | 15 days | 179SS
QA/QC registers and inspection logs. | 15 days | 180SS
Handover & Acceptance | 13 days
Final joint inspection. | 3 days | 176
Punch list clearance. | 7 days | 183
Issuance of Completion Certificate. | 3 days | 184
Training | 30 days
Technical training for Employer’s engineers on GIS, protection, SCADA, batteries, and transformer operations. | 30 days | 158
Demobilization | 14 days
Removal of temporary facilities, waste disposal, rehabilitation of access roads. | 7 days | 182
Site restoration to agreed condition. | 7 days | 189